WESTERN PACIFIC UNIVERSITY

CMN224 / CMP224 Software Engineering — Week 3

# Lab 3: Lifecycle Selection & Increment Plan

Formative (ungraded) · Moodle-enabled · output feeds Task 2 Part 2 directly

| Item | Details |
| --- | --- |
| Linked to | Week 3 lecture — Software Process Models (ULO2, ULO3) |
| Work mode | Individually, on the SAME client scenario you chose for Task 2 |
| Time | About 90 minutes |
| Submission | Completed worksheet uploaded to Moodle AND committed to week03/ in your Git portfolio |
| Why it matters | Section C of this worksheet is a first draft of Task 2 section 2.3 (work schedule). Do it properly now and Week 8 gets much easier. |

## Purpose

In the lecture you met six ways to organise the same four activities, and six questions that decide which one fits. Now you apply that decision to a real client — yours. There is no single correct model; the marks in Task 2 (and the exams) come from the quality of your justification.

## Part A — Apply the six selection questions (30 min)

For each question, answer for YOUR client scenario (Kina Ridge Primary School or Waghi Valley Produce Cooperative) and say what it pushes you toward.

| # | Selection question | Your answer for this client | Pushes toward… |
| --- | --- | --- | --- |
| 1 | How well understood are the requirements? | The school knows they need student records, attendance tracking, and reports, but some features may change after they see the system. | Incremental Development |
| 2 | Can the client engage continuously? | Yes, the head teacher and admin staff can give feedback during the project, but not all the time because of schoolwork. | Incremental / Agile |
| 3 | What does the contract or funding demand? | The client will want to see progress regularly and know that the project is moving forward. | Incremental with reviews |
| 4 | How big is the team, and where is it? | The team is small and may not always work in the same place, so regular communication is important. | Incremental Development |
| 5 | What is the cost of failure? | If student records are lost or entered incorrectly, it can create problems for the school. | Structured Incremental Approach |
| 6 | How fast must value appear for this client? | The school wants to start using the system as soon as possible instead of waiting until everything is finished. | Incremental Development |

## Part B — Choose and justify (15 min)

Chosen lifecycle: _______________________________________________  (may be a blend — say so explicitly)

In 150–200 words, justify the choice using your Part A answers. Name at least one factor that argues AGAINST your choice, and say how you will manage it.

Chosen Lifecycle: Incremental Development I chose the Incremental Development model for Kina Ridge Primary School because it allows the system to be built and delivered in smaller parts. This means the school can start using important features earlier while the rest of the system is still being developed. It also gives teachers and administrators a chance to provide feedback so improvements can be made in later stages. The requirements are mostly clear, but some details may change once the staff start using the system. Incremental development is suitable because changes can be made more easily without affecting the whole project. It also reduces risk since each part can be tested before moving on to the next one. One challenge with this approach is that school staff may not always have time to provide feedback because they are busy with teaching and administrative work. To manage this, meetings and feedback sessions will be planned at suitable times. Overall, incremental development is a practical choice because it provides early value and allows flexibility for future improvements.

Blends are professional, not a cop-out. "Incremental delivery internally, phase milestones reported to the board" is a legitimate and common answer in PNG work — provided you explain how the two fit together.

## Part C — Plan three increments (35 min)

Split your client's system into three increments. Increment 1 must be genuinely usable on its own — something the client could put to work the day you hand it over.

| Increment | What it delivers | Why THIS order (risk or value?) | Rough duration & why |
| --- | --- | --- | --- |
| 1 | Student Registration and Student Records | This is the most important part of the system because everything else depends on student information being available. | About 3 weeks because the database and basic functions need to be created and tested. |
| 2 | Attendance tracking and teacher records. | Once student records are working, attendance can be recorded and managed more easily. | About 2 weeks because it builds on the work completed in Increment 1. |
| 3 | Reports, student performance summaries, and admin dashboard. | These features need data from the first two increments before they can work properly | About 2 weeks because most of the required information will already be stored in the system. |

### C4. Delivery-condition check

For each increment, note one PNG delivery condition that affects when or how you can deliver it (client travel, power, connectivity, harvest or school-term timing, committee approval cycles).

Condition notes

Increment 1: Meetings may be difficult and need to fit around the school timetable. Increment 2: Power cuts-off or internet problems that could definitely affect testing. Increment 3: Final approval may be needed from the school administration before deployment.

## Part D — Reflect (10 min)

- If the client suddenly demanded ALL three increments by the same original deadline, which corner of the dependency triangle would you push back on, and what exactly would you say to them?

- Which of your three increments is most likely to change after the client sees increment 1? What does that tell you about how firmly to specify it now?

Your answers

I would push back on the scope of the project. I would explain that trying to finish every feature by the same deadline could affect the quality of the system. I would suggest focusing on the most important features first, such as student records and attendance tracking, and leaving less important features for a later update.

Increment 3 is most likely to change. After the school starts using the system, they may ask for different report formats or additional dashboard features. This shows that the details for Increment 3 should stay flexible until more feedback is received from users.

## Submitting

- Save as Lab3_<YourName>.docx and upload to Moodle → Week 3 → Lab 3.

- Copy it into week03/ in your portfolio and commit:

git add week03/ && git commit -m "Add Lab 3 lifecycle selection and increment plan"

- Keep it open when you start Task 2 Part 2 — Parts B and C become sections 2.3 and 2.4.