WESTERN PACIFIC UNIVERSITY

CMN224 / CMP224 Software Engineering — Assessment

Task 2: Requirements & Estimation Report

Scenario A – Kina Ridge Primary School Fee-Tracking System

Submitted By: Raygan KUTA

Student ID: 00271

Date Submitted: October 10, 2026

Semester II, 2026

1.1 Purpose and Scope

Purpose

The main aim of this system is to ensure that Kina Ridge Primary School has an effective digital fee tracking system that will be able to record the payments made by the students, track fee balances, create receipts, and generate reports for school administration.

This system will help reduce errors associated with manual recording of data.

Scope

The software will be able to:

•	Store information on students and parents.

•	Keep records of fees paid using cash deposits, bank deposits, and mobile money.

•	Provide payment receipts.

•	Keep records of fee balances and arrears.

•	Prepare financial reports to the school management and board.

•	Maintain security of all fee-related transactions.

Out of Scope

The software will not be able to:

•	Handle online payment transactions.

•	Manage academic performance.

•	Manage attendance of students.

•	Manage any learning related activities.

1.2 Business Context and Stakeholders

Business Context

There are about 450 students enrolled at Kina Ridge Primary School. At present, there are two ways used for keeping track of payments, exercise books and Excel sheets. Payment is made by several means including cash payments, bank deposits, and mobile money. There are power shortages weekly. Internet is normally accessible. This school needs better tracking of arrears and more dependable receipt printing.

Stakeholder Analysis

| Stakeholder | Role | Needs |
| --- | --- | --- |
| Bursar | Primary User | Enter payments correctly and produce receipts |
| Office Assistants | Daily Users | Search for students’ records and enter payment details |
| Head Teacher | Management | Monitor fee collection performance and arrears |
| School Board | Governance | Get term financial statements |
| Parents/Guardians | Fee Payers | Produce accurate payment records and receipts |
| Students | Beneficiaries | Make sure that payments are entered correctly |
| System Administrator | Technical Support | Manage users and backups |

1.3 Functional Requirements (MoSCoW Prioritised)

Must Have

FR1: The system will hold data about the students, which includes student number, name, class, and guardian information.

FR2: The system will store cash fee payments made by the student.

FR3: The system will store fee payments made using bank deposits.

FR4: The system will store fee payments made using mobile money.

FR5: The system will calculate outstanding balances automatically.

FR6: The system will generate unique payment receipts.

FR7: The system will have authorised user search ability of student payment information.

FR8: The system will generate arrears report.

FR9: The system will keep a full record of all payment transactions.

FR10: The system will function during internet disconnection.

Should Have

FR11: The system will have term financial reports generation ability.

FR12: The system will have receipt printing ability.

FR13: The system will have report exporting to PDF.

Could Have

FR14: The system will have SMS reminder for unpaid fee.

FR15: The system will have payment trend charts.

Won’t Have (Current Release)

FR16: The system will not support online fee payment process.

FR17: The system will not support mobile application.

1.4 Non-Functional Requirements

Performance

NFR1: Records of payments shall be saved within 3 seconds.

NFR2: Searching students shall take up to 5 seconds.

NFR3: Generating reports shall take up to 10 seconds.

Reliability

NFR4: System shall ensure 99% of data accuracy.

NFR5: System shall provide automatic generation of daily backups.

Security

NFR6: Access to the system shall be done using usernames and passwords.

NFR7: Only authorized personnel shall have access to financial data.

NFR8: Transactions shall be recorded for auditing purposes.

Usability

NFR9: Staff members who receive one-hour training shall be able to work with the system.

NFR10: User interface shall feature clear labels and convenient navigation.

Delivery conditions for PNG

NFR11: System shall continue working during restoration of power supply using saved records.

NFR12: System shall allow offline record input when connectivity is lost temporarily.

NFR13: System shall synchronize records after restoration of connectivity.

NFR14: System shall run efficiently on existing office laptop of the school.

NFR15: System shall enable printing receipts using existing printer.

1.5 Constraints and Business Rules

Constraints

1.	The current system only has an office laptop at school.

2.	The system utilizes a shared printer.

3.	Power outages take place every week.

4.	The payment for fees can be made through various modes of payment.

5.	The proposed solution should make use of existing resources in the school.

Business Rules

BR1: All payments should be associated with registered students.

BR2: Each payment will create a new receipt number.

BR3: The fee balances of all students will be updated instantly upon payment entry.

BR4: There will be fee arrears report for the head teacher.

BR5: Board summary report will be created at the end of each term.

BR6: Records of finance cannot be permanently deleted.

1.6 Glossary

| Term | Definition |
| --- | --- |
| Fee Arrears | Outstanding school fees not yet paid |
| Receipt | Official proof of payment |
| Bursar | School officer responsible for fee collection |
| Guardian | Parent or person responsible for paying fees |
| Transaction | A recorded payment activity |
| Student Record | Information relating to a student |
| Balance | Remaining fee amount owed |
| Term Report | Financial summary prepared each school term |

Part 2 – Estimate and Work Schedule

2.1 Task Breakdown

| Task | Description |
| --- | --- |
| Requirements Analysis | Gather and document requirements |
| System Design | Database and interface design |
| Database Development | Student and payment database |
| Student Management Module | Student record management |
| Payment Processing Module | Recording fee payments |
| Receipt Module | Receipt generation and printing |
| Reporting Module | Arrears and board reports |
| Security Module | Login and access control |
| Backup Functionality | Data backup and recovery |
| Testing | System verification and validation |
| Deployment | Installation and configuration |
| User Training | Staff training |

2.2 Time Estimates

Estimation Technique

Three-point estimation:

Estimated Time = (Optimistic + 4 × Most Likely + Pessimistic) ÷ 6

| Task | O | M | P | Estimated Days |
| --- | --- | --- | --- | --- |
| Requirements Analysis | 3 | 5 | 7 | 5 |
| System Design | 3 | 5 | 7 | 5 |
| Database Development | 4 | 6 | 8 | 6 |
| Student Module | 3 | 5 | 7 | 5 |
| Payment Module | 5 | 7 | 9 | 7 |
| Receipt Module | 2 | 4 | 6 | 4 |
| Reporting Module | 4 | 6 | 8 | 6 |
| Security Module | 2 | 3 | 5 | 3.2 |
| Backup Module | 2 | 3 | 4 | 3 |
| Testing | 5 | 7 | 10 | 7.2 |
| Deployment | 2 | 3 | 4 | 3 |
| Training | 2 | 3 | 5 | 3.2 |

Total Estimated Duration

Approximately 57 person-days (about 11-12 weeks for one developer).

Assumptions

- One full-time developer is assigned.

- School staff are available for meetings.

- Requirements do not change significantly.

- Existing laptop and printer remain operational.

- Basic technical support is available during deployment.

2.3 Work Schedule

| Week | Activity | Client Deliverable |
| --- | --- | --- |
| Week 1 | Requirements Gathering | Approved Requirements |
| Week 2 | System Design | Design Documentation |
| Week 3 | Database Development | Database Prototype |
| Week 4 | Student Management Module | Student Records System |
| Week 5 | Payment Processing Module | Payment Recording Functions |
| Week 6 | Receipt Generation Module | Receipt Printing System |
| Week 7 | Reporting Module | Arrears Reports |
| Week 8 | Security and Backup Features | Secure Data Management |
| Week 9 | System Testing | Tested System |
| Week 10 | Bug Fixing | Updated System |
| Week 11 | Deployment | Live System |
| Week 12 | Training | Trained Staff |

Milestones

Milestone 1: Requirements Approved (Week 1)

Milestone 2: Core Fee Tracking Completed (Week 6)

Milestone 3: Reporting Features Completed (Week 7)

Milestone 4: Testing Completed (Week 9)

Milestone 5: Deployment and Training Completed (Week 12)

2.4 Dependency Triangle Analysis

Option 1: Fixed Scope

All planned features are delivered.

Advantage: Complete solution.

Disadvantage: Increased time and development cost.

Option 2: Fixed Time

Essential features are delivered first.

Advantage: Faster implementation.

Disadvantage: Some advanced features may be delayed.

Option 3: Fixed Cost

Development remains within a fixed budget.

Advantage: Predictable spending.

Disadvantage: Reduced functionality.

Recommended Option

Fixed Time with Prioritised Scope is recommended.

The school's biggest concern is visibility of fee arrears and trustworthy receipts. Therefore, the first release should include:

- Student Management

- Payment Recording

- Receipt Generation

- Arrears Reporting

Additional features such as SMS reminders and advanced reporting can be introduced in later releases.

This approach delivers the most important business value early while controlling project risk and cost

AI Use Declaration

This document has been produced with the help of Microsoft Copilot in terms of drafting, proofreading, structuring, and formatting. All the analysis of requirements, stakeholders’ identification, prioritization, estimation calculations, scheduling, and recommendation have been verified by the student.